## Introduction
a | Background
The contracting process has many moving parts with a lengthy life cycle, requiring multiple steps and a range of stakeholders across different departments and organizations. Tracking progress toward milestones allows program officials to monitor the status at each step and check for any issues causing delays and take necessary action. Similarly, timely payments to service providers is critical to ensure uninterrupted TB care to patients. Timely payments do not just enhance the financial stability of the service provider, but also help to build trust needed to foster a long-term business relationship between the procuring entity and service provider.
b | Purpose of the tool (what is it for?)
This excel-based tool contains two trackers: 1) Contracts Tracker and 2) Payments Tracker. The purpose of this contracts tracker is to monitor progress toward engagement of private-sector partnerships by tracking the contracting of targeted services approved under the ROP, starting from the budget approval in the ROP to the time of contract signing. The purpose of the payments tracker is to monitor the turnaround time (TAT) of payments once a contract has been established to enhance timely and accurate payment. The tool captures the status of meeting various milestones in the payment process by tracking invoices generated against the terms and timelines stipulated in contracts.
c | Structure of the tool (What is the purpose of each of the tabs, and how do they relate to each other?)
The tool has been divided in to six sheets and description of every sheet is given in the table below. Users will update them.
| Name of sheet | Description
| SOP | Describes the different sheets/tabs in the document and defines all data capture fields in the sheets.
| Change log | Records the changes made in the document by any user.
| Contract Target_Value | Records the details of Contracts done in the States. One row depicts one unique contract.
| Contracts Tracker | Records the details of all individual contract.
| District Info Contracts | Records the names and numbers of districts covered in state-level contracts that cover multiple districts.
| Payments Tracker | Records the details of all individual invoices.
Detailed information is given in the adjacent sheet (i.e., SOP) explaining the definition, data entry, source of data, and type of data input for every data element mentioned in the tracker (i.e. contract tracker and payment tracker).
d | How to use the tracker?
Instructions for data entry is covered in the adjacent sheet (i.e., SOP) under general guidelines for data entry.
e | Who can use this tool?
This tool can be used by people who are involved in the procurement/contracting of services and processing of payment at state/district level.
| Name of sheet | Intended user
| SOP | All persons who are operating the tool
| Change log | All persons who are operating the tool
| Contract Target_Value | Person intended to manage the contracting of services at state/district level
| Contracts Tracker | Person intended to manage the contracting of services at state/district level
| District Info Contracts | Person intended to manage the contracting of services at state/district level
| Payments Tracker | Person intended to manage the contracting of services at state/district level
f | Data updated in the tracker
Data to be updated as per the given schedule.
| Name of sheet | Frequency
| Change log | As and when any data element is revised/changed from the original entry value
| Contract Target_Value | Once or twice in a year based on approval of ROP and supplementary ROP
| Contracts Tracker | Fortnightly
| District Info contracts | As and when any new state level contract covering multiple districts updated in the tracker
| Payments Tracker | Fortnightly
g | Output of the tool and its use
The contract tracker is used to record, monitor, and analyze pre-contracting TAT for accomplishing each major milestone until signing of contract. The payment tracker documents reasons for late submissions, penalties, invoice rejections, late payments, etc. to inform users on what needs to be improved to reduce payment TAT.

## SOP
General guidelines
Enter data manually; i.e., DO NOT copy/paste fields, especially columns that capture Date or Amount. For a Date column, double click on the cell to open the calendar and then select a date. For Amounts, click on the cell and enter the numbers.
To have figure amounts separated by hundreds, as in the Indian currency system, go to: >> File>> Options >>Regional format settings >> English (India) >> Save.
Roles: Contract Management Expert to update and maintain the Contracts-related sheets; Public Finance Management Expert to update and maintain the Payments tracker, MEL Advisor to analyze data, and Team Leads to ensure quality of data and review of contracting and payment efficiencies.
In text fields, write "not applicable" or "no data available" as relevant. In date, amount, and number fields, write "not applicable" or "no data available" in comments or remarks column. No data available: absence of information/data; Not applicable: question is not relevant or does not apply to the given context
Statutory deductions are not included in the payment tracker.
Definitions—Contracts Tracker
Column | Data element | Definition | Entry | Source of data | Type of field | Remarks
A | S.No. | Serial number |  |  | Text
B | State | Name of the state | Enter full name of the state. |  | Text
C | Level of contract | Level of authority where the memorandum of understanding (MOU) is signed, not the level where services are to be provided | Choose one from state or district. | Contract document | Text (dropdown) | For example, if the MOU is between District A and the Provider, and the service provision is at the village level, then the level of contract is "District."
D | Source of approval: ROP/Non-ROP | Whether the contract is within the approved contracts in the record of proceedings (ROP), or it is a contract outside the purview (not budgeted) of ROP | Choose one from ROP and Non-ROP. | ROP | Text (dropdown)
E | FY of ROP (yyyy–yyyy) | Financial year of the ROP within which the contract is approved | Enter FY in yyyy–yyyy format. | ROP | Text
F | Type of contract | Type of the contract based on the payment modalities | Choose one from: Input/Output/Fee for service/Hybrid/Grant-In-Aid/Non-Financial. | Contract document | Text (dropdown)
G | Name (in case of district-level contract) OR number of districts covered (in case of multiple districts) | Name of the district if it is a district-level contract OR number of districts covered in the multiple-district state-level contract. (Additionally mention the details in the sheet "District Info Contracts") |  | Contract document | Number
H | Instrument of contract | Instrument used to formalize the engagement between the procuring entity and service provider | Choose one from: Memorandum of agreement (MOA), Memorandum of understanding (MOU), Service-level agreement, or Work order. | Contract document | Text (dropdown)
I | Type of services | Type of TB care/support service for which the contract is made | Choose one from: Advocacy, communication, and social mobilization (ACSM), Airborne infection control (AIC), Annual maintenance contract (AMC), Chest x-rays (CXR), Designated microscopy centre (DMC), Extrapulmonary TB (EPTB), First-line line probe assay (FLLPA), Interferon-Gamma Release Assay (IGRA), Others, Public health action (PHA), Patient Provider Support Agency (PPSA), Treatment services, TSU, TU, Active case finding and TB prevention, Comprehensive maintenance contract (CMC), HR Support Services. | Contract document | Text (dropdown)
J | Source of funding | Source of funding for the contracting of services | Choose one from: Corporate Social Responsibility (CSR), District Mineral Foundation (DMF), Loan, National Health Mission (NHM), Other, ROP, Status, Fifteenth Finance Commission (XVFC). | Program division/NTEP | Text (dropdown)
K | Thematic area 1 | Additional services under bundled under same contract | Choose one from: Active case finding and TB prevention, Adherence, Airborne infection kit, Diagnostics, DRTB Consul TAT, IEC, Innovations, LT Scheme, Maintenance, PPSA, Specimen transport, Treatment services, X-ray services, Other. | Contract document | Text (dropdown)
L | Thematic area 2 | Additional services under bundled under same contract | Choose one from: Active case finding and TB prevention, Adherence, Airborne infection kit, Diagnostics, DRTB Consul TAT, IEC, Innovations, LT Scheme, Maintenance, PPSA, Specimen transport, Treatment services, X-ray services, Other. | Contract document | Text (dropdown)
M | Contract ID (composition of ID) | Unique ID with maximum six characteristics. First two letters represents status name, next two characters represent "type of service" and last two letters represent serial number of the contract with in the partnership. | Status codes: Andhra Pradesh = AP; Delhi = DL, Gujarat = GJ, Odisha = OD, Telangana = TS, Haryana = HR, Punjab = PB, Jharkhand = JH Service code: ACSM: AS; Active case finding and TB prevention: AC; AIC: AI ; AMC: AM; CXR: CX; DMC : DM; EPTB: EP; FLLPA: FL; IGRA: IG; Others :OR; PHA: PH; PPSA: PP; Treatment services: TS; TSU: TT; TU: TU; CMC: CM; HR Support Services: HR Serial number of contract: starts from 01 to 99 | User to define the ID |  | Example: APPP01
N | Operational status | Current operational status of the contract. Operational contract refers to a contract that has started service provision on ground. | Choose one from: Operational and Not operational. | Contract document | Text (dropdown)
O | If not operational, current status | Status of the contract if it is not operational. This is the stage in the pipeline where the contract currently is. | Choose one from: RFP preparation, RFP published, Pre bid meeting, Bid closing, Technical Evaluation, Financial Evaluation, Agency Selected, Letter of acceptance, Retender, Under renewal, Not Applicable, No data available, Dropped. | NTEP/program division | Text (dropdown)
P | ROP approval date, if any (dd-mm-yyyy) | Date of ROP approval by the stated government to solicit bids or proposals from qualified vendors or service providers for a specific project, service, or procurement. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
Q | RFP development start date (dd-mm-yyyy) | Date on which Request for Proposal (RFP)/MOU development started (i.e. 1st meeting of RFP committee/procurement committee); the development of an RFP involves defining scope of work/project requirements, evaluation criteria, terms, and conditions. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
R | RFP approved by procurement committee date (dd-mm-yyyy) | Date on which the RFP received formal approval from the procurement committee within the government | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
S | RFP approved by competent authority date (dd-mm-yyyy) | Date on which the RFP was approved by the competent authority | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
T | RFP Publish date (dd-mm-yyyy) | Date on which the RFP is officially released or made public for potential vendors to review and submit their bids or proposals | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
U | Bid Closing date (dd-mm-yyyy) | Date on which the submission period for bids or proposals in response to an RFP officially ends. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
V | Technical Bid Opening date (dd-mm-yyyy) | Date on which the technical bids opened in the presence of RFP committee/bid evaluation committee and evaluation started for technical aspects (i.e. eligibility, qualifications, technology, tools etc.) of the bids/proposals submitted by the vendor | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
W | Financial Bid Opening date (dd-mm-yyyy) | Date on which the financial bids of qualified bidders opened in the presence of RFP committee/bid evaluation committee and the cost proposals from various vendors are analyzed to determine the most economically advantageous offer | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
X | Bid status Successful/Unsuccessful | Refers to the outcome of the bidding process, which culminates successfully with selection of an agency/vendor or ends unsuccessfully without selection of an agency/vendor due to various reasons such as failing to meet the technical or financial requirements. | Choose one from Successful and Unsuccessful. | NTEP/NHM file | Text (dropdown)
Y | Agency/vendor selection date (dd-mm-yyyy) | Date on which the agency or vendor was selected for the contract as a result of successful bidding process | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
Z | Name of the agency/vendor selected | Name of the vendor selected for the contract |  | Bidder document | Text
AA | Type of agency (Not for profit/For profit) | Registration/legal entity of the agency selected for the contract | Choose one from For Profit and Not for profit. | Bidder document | Text (dropdown)
AB | Date of Contract Signing (dd-mm-yyyy) | Date on which the contract is signed between the state/district and the vendor/agency. This is the final step in the procurement process where the government and the selected vendor formally sign the contract, outlining the terms, conditions, and agreements related to the project or services. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | Contract document | Date (dd-mm-yyyy)
AC | Date of operationalization (dd-mm-yyyy) | Date on which actual operations started on ground by the selected agency (as agreed in the contract) | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM File | Date (dd-mm-yyyy)
AD | Contract value (INR) | Total value of the contract/MoU. It refers to the total monetary worth of the contract, representing the agreed-upon financial obligations and commitments. | Enter amount in INR. | Contract document | Amount (in two decimal places)
AE | Contract duration (Months) | Total duration of the contract in months. It refers to the time period during which the legal binding agreement between the government and agency is in effect. | Enter number of months. | Contract document | Number
AF | Contract End date (dd-mm-yyyy) | Date on which the contract will end. It refers to the official date when the contract's binding terms and obligations cease to be in effect. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | Contract document | Date (dd-mm-yyyy)
AG | Invoice submission frequency | Regularity with which the invoices should be sent to the government for payment. | Choose one from: Bi-Annually, Half-yearly, Monthly, No data available, Not applicable, Others, Quarterly. | Contract document | Text (dropdown)
AH | Time to submit invoice after reporting period (days) | Number of days after the service provision, after which the invoice must be submitted to the government, as given in the contract/MOU | Enter number of days. | Contract document | Number
AI | Time to pay the invoice as given in contract (days) Add Comment if no timeline is given | Number of days for the government to make payment after invoice submission, as given in the contract
AJ | Contract Renewal-1 date (dd-mm-yyyy) | Date of first contract renewal | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
AK | No. and type of changes in the contracting terms during renewal-1 | Number and type of changes that were made at the time of first contract renewal | Enter the number of changes and mention briefly the changes done in first renewal of the contract. | NTEP/NHM file | Text
AL | Contract value after renewal-1 | Contract value after first renewal of the contract | Enter contract value amount after first renewal. | NTEP/NHM file | Amount (in two decimal places) | It may or may not change from previous value.
AM | Contract end date after renewal-1 (dd-mm-yyyy) | New contract end date after first renewal of the contract | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
AN | Contract renewal-2 date (dd-mm-yyyy) | Date of second contract renewal | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
AO | No. and type changes in the contracting terms during renewal-2 | Number and type of changes that were made at the time of second contract renewal | Enter the number of changes and mention briefly the changes done in second renewal of the contract. | NTEP/NHM file | Text
AP | Contract value after renewal-2 | Contract value after second renewal of the contract | Enter contract value amount after second renewal. | NTEP/NHM file | Amount (in two decimal places) | It may or may not change from previous value
AQ | Contract end date after renewal-2 | New contract end date after second renewal of the contract | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell | NTEP/NHM file | Date (dd-mm-yyyy)
AR | Contract renewal-3 date (dd-mm-yyyy) | Date of third contract renewal | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | Date (dd-mm-yyyy)
AS | No. and type changes in the contracting terms during renewal-3 | Number and type of changes that were made at the time of third contract renewal | Enter the number of changes and mention briefly the changes done in third renewal of the contract. | NTEP/NHM file | Text
AT | Contract value after renewal-3 | Contract value after third renewal of the contract | Enter contract value amount after third renewal. | NTEP/NHM file | Amount (in two decimal places) | It may or may not change from previous value.
AU | Contract end date after renewal-3 | New contract end date after third renewal of the contract | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/NHM file | date (dd-mm-yyyy)
AV | Remarks | Enter any other comments to explain or justify. |  |  | Text
AW | TAT between ROP approval to RFP Publish | TAT between ROP approval to RFP Publish dates. Denotes time it takes for the government to finalize the ROP, get it approved, and then proceed to publish the RFP for potential bidders or contractors to respond. The goal is to minimize this time to expedite the procurement or project initiation process. |  |  |  | Calculated field
AX | TAT between RFP Publish to Bid Closing | TAT between RFP Publish to Bid Closing is a measure of how much time is provided to potential bidders to review the RFP, prepare their proposals, and submit them before the specified bid closing date. A well-defined and reasonable TAT is important to ensure that interested parties have sufficient time to prepare quality proposals and to promote a fair and competitive bidding process. |  |  |  | Calculated field
AY | TAT between Bid Closing to Tech Bid Open | TAT between Bid Closing to Tech Bid Open is a measure of the time it takes for the government to close the bid submission process, gather all submitted bids, and proceed to the next step of evaluating the technical aspects of the bids. A well-defined and efficient TAT is essential for maintaining transparency and adhering to the planned timeline in the overall procurement process. |  |  |  | Calculated field
AZ | TAT between Tech Bid Open to financial evaluation | TAT between Tech Bid open to Financial Evaluation is the time it takes for the government to complete the assessment of technical bids and initiate the evaluation of the financial aspects of the bids. Efficient coordination between technical and financial evaluations is crucial for making informed decisions in the procurement process. A well-managed TAT contributes to the overall effectiveness and speed of the procurement cycle. |  |  |  | Calculated field
BA | TAT between financial evaluation to Contract Sign | TAT between Financial Evaluation to Contract Sign is the time it takes for the government to conclude the financial evaluation, make a decision on the selected vendor, and complete the necessary administrative processes leading to the formal signing of the contract. A well-managed TAT in this phase is crucial for ensuring a smooth transition from the evaluation stage to the commencement of the contracted work or services. It reflects the efficiency of the procurement process and the government's ability to promptly move from bid evaluation to contract execution. |  |  |  | Calculated field
BB | TAT between ROP approval to Contract Sign | TAT between ROP approval to Contract sign is the time it takes for the government to complete the necessary steps following the approval of the ROP, including vendor selection, negotiation, and administrative processes leading to the formal signing of the contract. An efficient TAT in this phase is critical for initiating the project or services in a timely manner, minimizing delays, and ensuring a smooth transition from the planning stage to the execution of the contracted work. |  |  |  | Calculated field
BC | TAT between RFP published to vendor selection | TAT between RFP published to vendor selection is the time it takes for the government to go through the various stages of the procurement process, including bid submission, evaluation, and decision-making, leading to the selection of a vendor. A well-managed TAT in this phase is crucial for efficient project initiation, ensuring that the selected vendor can start work in a timely manner, and maintaining the overall schedule of the project or service delivery. |  |  |  | Calculated field
BD | TAT between RFP published to contract signed | TAT between RFP published to contract signed is the time it takes for the government to go through the various stages of the procurement process, including bid submission, evaluation, vendor selection, negotiation, and administrative processes leading to the formal signing of the contract. An efficient TAT in this phase is crucial for initiating the project or services in a timely manner and ensuring that all contractual details are finalized and agreed upon. |  |  |  | Calculated field
Definitions—Payments Tracker
Column | Data element | Definition | Entry | Source of data | Type of field | Remarks
A | S.no | Serial number |  |  | Number
B | State | Name of state for which the invoice has been raised |  |  | Text
C | District | Name of district for which the invoice has been raised |  |  | Text
D | Contract ID | Contract ID under which the invoice has been raised |  | Defined by user | Text | This should be the same as the type of services for the contract in Contracts tracker.
E | Name of the agency | Name of vendor/agency issuing the invoice |  | MOU | Text | This should be the same as the type of services for the contract in Contracts tracker.
F | Type of contract | Financial type of the contract | Choose one from: Input/Output/Fee for service/Hybrid/Grant-In-Aid. | MOU | Text (dropdown) | This should be the same as the type of services for the contract in Contracts tracker.
G | Type of services | Main type of service for which the contract is made | Choose one from: ACSM, AIC, AMC, CXR, DMC, EPTB, FLLPA, IGRA, Others, PHA, PPSA, Treatment services, TSU, TU, Active case finding and TB prevention, CMC, HR Support Services. | MOU | Text (dropdown) | This should be the same as the type of services for the contract in Contracts tracker.
H | Standard time (days) to submit invoice | Number of days after the service provision, after which the invoice must be submitted to the government | Enter number of days. If no timeline is provided in the contract, enter 30 as the standard. | MOU | Number
I | Contract FROM date (dd-mm-yyyy) | This signifies the date on which the contract officially comes into effect and all its terms become binding. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | MOU | Date (dd-mm-yyyy)
J | Contract TO date (dd-mm-yyyy) | This refers to the date on which the contract officially ends and is no longer in effect. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | MOU | Date (dd-mm-yyyy)
K | Year (of invoice submitted) | Calendar year in which the services were provided and for which the invoice has been raised | Mention year in yyyy format. | Invoice | Text
L | Quarter No./Period (of invoice period) | Quarter in the calendar year in which the services were provided and for which the invoice has been raised. Follow Indian FY Quarters i.e. Q1=Apr-Jun | Mention the quarter( Q1,Q2,Q3,Q4) (text field). If the invoice submitted for a quarter and is for some other period, mention the period (since it is a text field, other data entry is allowed). | User to define | Text | The invoice can be for more than one quarter, in which case quarters separated by commas can be written.
M | Invoice No. | Unique identifier assigned to an invoice document |  | Invoice | Text
N | Invoice period FROM date (dd-mm-yyyy) | Start date of the specific time frame for which an invoice is being generated. It marks the beginning of the period during which services were provided, and for which payment is being requested. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | Invoice | Date (dd-mm-yyyy)
O | Invoice period TO date (dd-mm-yyyy) | End date of the specific time frame for which an invoice is being generated. It marks the end of the period during which services were provided, and for which payment is being requested. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | Invoice | Date (dd-mm-yyyy)
P | Invoice submission DUE date (calculated field) (dd-mm-yyyy) | Deadline by which an invoice must be submitted to the government for payment | Calculated field | Invoice | Date (dd-mm-yyyy)
Q | Date of invoice submitted to NTEP (dd-mm-yyyy) | Specific date the agency sent the invoice to the government. It marks the official initiation of the billing process and triggers their obligation to review and process the invoice for payment. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | Invoice | Date (dd-mm-yyyy)
R | Revised invoice submission date, if any (dd-mm-yyyy) | Date of submission of a revised invoice by the agency | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | Invoice | Date (dd-mm-yyyy) | This could be due to several reasons, such as missing information, delays in work completion, errors in the invoice, etc.
S | Number of times invoices submitted in case of resubmission | Number of times that the invoice had been asked for revision before allowing a final submission | Enter number. |  | Number
T | Reason for late submission of invoice (at least 3 key reasons) | Justification and reasons given by the agency for late submission of invoices. Capturing this information helps to analyze the common reasons and find ways to eliminate them. | Write at least three reasons. |  | Text
U | Invoice amount (in INR) | Total amount billed by the agency to the government for providing services in the period | Write amount in INR. | Invoice | Amount (in two decimal places)
V | Invoice status (Accepted/Rejected) | It refers to the status of invoice acceptance by the government. An accepted invoice will go for further processing and payments while a rejected invoice will not be paid by the government. | Choose one from Accepted and Rejected. | NTEP/Program division/NHM file | Text (Dropdown)
W | Reason for rejection, if rejected | Specific explanation given by the government for refusing to pay an invoice the agency submitted. It potentially outlines what needs to be corrected at the agency level to get the future invoices accepted. |  | NTEP/Program division/NHM file | Text | An invoice could be rejected for reasons such as late submission, duplicate invoice, dispute over charges, contractual discrepancies, etc.
X | Validation completed date by NTEP (dd-mm-yyyy) | Date on which the invoice validation process is completed by the government through different verification methods such as calling or meeting patients | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/Program division/NHM file | Date (dd-mm-yyyy)
Y | Invoice amount approved | Final amount approved by the government which will be paid to the agency | Write amount in INR. | NTEP/Program division/NHM file | Amount (in two decimal places)
Z | Invoice amount approved date (dd-mm-yyyy) | Specific date when the final amount was approved by the government for further processing | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/Program division/NHM file | Date (dd-mm-yyyy)
AA | Penalty amount INR (write 0 if no penalty) | Deductions based on specific "penalty" clauses in the MOU | Write amount in INR. Write 0 if no penalties were incurred. | NTEP/Program division/NHM file | Amount (in two decimal places) | Penalty clauses include specific deduction of certain amounts, such as 1% penalty for less than 80% achievement, or INR 10,000 deduction for late submission, etc.
AB | Reason for penalty in payment | Reasons due to which penalty was laid to the invoice | Write reasons. | NTEP/Program division/NHM file | Text
AC | Deduction amount for invoice calculation error INR (write 0 if not deduction) | Deductions made to the invoice amount submitted by the agency on account of errors in the invoice such as inaccurate calculations, over-charging etc. The deductions are not specifically mentioned under the "penalty" clauses of the MOU. | Write amount in INR. Write 0 if no deductions were made. | NTEP/Program division/NHM file | Amount (in two decimal places)
AD | Reason for deduction | Reasons for which the deductions were made | Write reasons. | NTEP/Program division/NHM file | Text
AE | Invoice payment received date (dd-mm-yyyy) | Specific date on which the agency received payment for an issued invoice. It marks the completion of the financial transaction and signifies that the government has fulfilled their obligation to pay for the services provided. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/Program division/NHM file | date (dd-mm-yyyy)
AF | Invoice amount received (in INR) | Total amount received by the agency for the issue invoice | Write amount in INR. | NTEP/Program division/NHM file | Amount (in two decimal places)
AG | Date of total invoice amount received, in case of partial payments (dd-mm-yyyy) | In cases where partial payments are made against a certain invoice, this refers to the specific date, when the complete payment (last instalment) was made to the agency. | Enter date by double clicking in the cell and selecting a date. If date is not available, mention the Status/reason by inserting a comment in the cell. | NTEP/Program division/NHM file | Date (dd-mm-yyyy)
AH | Reasons for delayed payment (at least 3 key reasons) | Reasons cited by the government for late payment | Write reasons. | NTEP/Program division | Text
AI | Time (days) taken for invoice submission (from submission due date) | This is determined by the difference between the submission due date and the actual date when the invoice is received by the government. A shorter time taken for invoice submission reflects a prompt and organized invoicing process, whereas a longer time may indicate delays, potential issues in the submission process, or challenges in the communication of submission deadlines. |  |  | Calculated field
AJ | TAT between invoice submission to payment | Duration, in days , between the submission of an invoice by the agency and the subsequent payment made by the government. This metric is crucial in assessing the efficiency of the accounts payable process and the time it takes for the government to validate invoices and run various administrative processes to settle its financial obligations with vendors or service providers. |  |  | Calculated field
AK | Payment completeness ratio (against approved amount) | Financial metric to the ratio or percentage of a payment made in comparison to the initially approved or authorized amount. This metric is relevant in financial management and procurement processes, providing insights into how closely actual payments align with the initially agreed-upon or approved amounts. |  |  | Calculated field
AL | Remarks, if any | Enter any other comments related to the invoice.

## Change Log
S.No | Last updated | Sheet updated | Update made by | Details of update | Remarks
| Date of change made | Name of sheet updated | Name of person who updated the sheet | Provide details of the update made (e.g., entered data, corrected data, entered a new contract, created a new report required by the State, etc.) | Enter any other remarks

## Contract Targets_Value
Contracts Achievement and Values
Year | State | Total districts in the State | Contract/Services Type | Target | Achievement | Gap | Districts target | District achievement | District gap | Contract Value | Remarks
FY | Name of the state | Number of districts in the state | Type of contract, whether PPSA or Non-PPSA | Target of contracts to be done as defined in the ROP | Targets achieved in the FY | Field shows the gap in achievement | Number of districts targeted to be covered in the contract | Number of districts covered (actual) by the contracts | Field shows the gap in achievement | Total value of the contract INR in Lakhs—amount mentioned in the MOU/MOA-Mention (full contract value, not by year—calculate in the year the MOU was signed)
2019–2020 |  |  | PPSA |  |  | 0 |  |  | 0
2019–2020 |  |  | Non-PPSA |  |  | 0 |  |  | 0
2020–2021 |  |  | PPSA |  |  | 0 |  |  | 0
2020–2021 |  |  | Non-PPSA |  |  | 0 |  |  | 0
2021–2022 |  |  | PPSA |  |  | 0 |  |  | 0
2021–2022 |  |  | Non-PPSA |  |  | 0 |  |  | 0
2022–2023 |  |  | PPSA |  |  | 0 |  |  | 0
2022–2023 |  |  | Non-PPSA |  |  | 0 |  |  | 0
2023–2024 |  |  | PPSA |  |  | 0 |  |  | 0
2023–2024 |  |  | Non-PPSA |  |  | 0 |  |  | 0
2024–2025 |  |  | PPSA |  |  | 0 |  |  | 0
2024–2025 |  |  | Non-PPSA |  |  | 0 |  |  | 0
Budget in Lakhs INR
| Total ROP Value—PPSA | Total ROP Value—NGO PPP scheme
FY 22–23
FY 23–24
FY 24–25
FY 25–26
Source: ROP Document

## Contracts Tracker
S.No. | State name | Level of contract | Source of approval: ROP/Non-ROP | FY of ROP (yyyy–yyyy) (when the ROP was approved) | Type of contract | Name of district (in case of district-level contract) OR Number of districts covered (in case of multiple districts) | Instrument of contract | Type of services | Source of funding | Thematic area 1 | Thematic area 2 | Contract ID (composition of ID) | Operational status | If not operational, current status | ROP approval date, if any (dd-month-yyyy) | RFP/MOU development start date (dd-month-yyyy) | RFP approved by procurement committee date (dd-month-yyyy) | RFP approved by competent authority date (dd-month-yyyy) | RFP Publish date (dd-month-yyyy) | Bid Closing date (dd-month-yyyy) | Technical Bid Opening date (dd-month-yyyy) | Financial Bid Opening date (dd-month-yyyy) | Bid status Successful/Unsuccessful | Agency/vendor selection date (dd-month-yyyy) | Name of the agency/vendor selected | Type of agency (Not for profit/For profit) | Date of Contract Signing (dd-month-yyyy) | Date of operationalization (dd-month-yyyy) | Contract value (INR) | Contract duration (months) | Contract end date (dd-month-yyyy) | Invoice submission frequency | Time to submit invoice after reporting period given in contract (days) Add in comment if no timeline is given | Time to pay the invoice as given in contract (days) Add in comment if no timeline is given | Contract renewal-1 date (dd-month-yyyy) | No. and type of changes in the contracting terms during renewal-1 | Contract value after renewal-1 | Contract end date after renewal 1 (dd-month-yyyy) | Contract renewal-2 date (dd-month-yyyy) | No. and type changes in the contracting terms during renewal-2 | Contract value after renewal-2 | Contract end date after renewal-2 (dd-mm-yyyy | Contract renewal-3 date (dd-month-yyyy) | No. and type changes in the contracting terms during renewal-3 | Contract value after renewal-3 | Contract end date after renewal-3 (dd-month-yyyy) | Remarks | TAT between ROP approval to RFP Publish | TAT between RFP Publish to Bid Closing | TAT between Bid Closing to Tech Bid Open | TAT between Tech Bid Open to Financial Evaluation | TAT between Financial Evaluation to Contract Sign | TAT between ROP approval to Contract Sign | TAT between RFP Publish to vendor selection | TAT between RFP Publish to Contract Sign | TAT between RFP drafting to Contract Sign

## District Info Contracts
This sheet captures the names of the districts covered in state-level contracts that cover multiple districts.
Enter one district in one row; for example, if a contract covers 11 districts, the data entry will be done in 11 rows. The name of district will change in each row; however, all other cell values will remain the same.
State | Contract ID | Type of Services (PPSA/Non-PPSA) | Name of district | Date of operationalization | Sample data entry
[6 empty] | State | Contract ID | Type of services | Name of District | Date of operationalization
[6 empty] | Andhra Pradesh | APPP01 | PPSA | ANANTHAPURAMU | 2023-11-09
[6 empty] | Andhra Pradesh | APPP01 | PPSA | EAST GODAVARI | 2024-01-05
[6 empty] | Andhra Pradesh | APPP01 | PPSA | GUNTUR | 2023-12-12
[6 empty] | Andhra Pradesh | APPP01 | PPSA | KRISHNA | 2023-10-19
[6 empty] | Andhra Pradesh | APPP01 | PPSA | PRAKASAM | 2023-08-04

## Payments Tracker
S.no | State | District/Zone/Cluster | Contract ID | Name of agency | Type of contract | Type of services | Standard time (days) to submit invoice | Contract FROM date (dd-month-yyyy) | Contract TO date (dd-month-yyyy) | Year (of invoice period) | Quarter No./Period (of invoice period) Follow Indian FY Quarters i.e. Q1=Apr-Jun | Invoice No. | Invoice period FROM date (dd-month-yyyy) | Invoice period TO date (dd-month-yyyy) | Invoice submission DUE date (calculated field) | Date of invoice submitted to NTEP (dd-month-yyyy) | Revised invoice submission date, if any (dd-month-yyyy) | Number of times invoices submitted in case of resubmission | Reason for late submission of invoice (at least 3 key reasons) | Invoice amount (in INR) | Invoice status (Accepted/ Rejected) | Reason for rejection, if rejected | Validation completed date by NTEP (dd-month-yyyy) | Invoice amount approved | Invoice amount approved date (dd-month-yyyy) | Penalty amount INR (write 0 if no penalty) | Reason for penalty in payment | Deduction amount for invoice calculation error INR (write 0 if not deduction) | Reason for deduction | Invoice payment received date (dd-month-yyyy) | Invoice amount received (in INR) | Date of total invoice amount received, in case of partial payments (dd-month-yyyy) | Reasons for delayed payment (at least 3 key reasons) | Time (days) taken for invoice submission (from submission due date) | TAT between invoice submission to payment | Payment completeness ratio (against approved amount) | Remarks, if any

## Dropdown (hidden)
SN | State Name | District Name | ROP/Non-ROP | Type of contract | Process of contract/Instrument of contract | Level of Contract | Type of services | Source of funding | Thematic Area 1 | Thematic Area 2 | Thematic Area 3 | Thematic Area 4 | Thematic Area 5 | Contract ID (Composition of ID) | Operational status | If not Operational, current status | Needs Assessment submission date, if any | RoP Approval date, if any | RFP/ MoU development start date | RFP approved by Procurement committee (Date) | RFP approved by competent Authority (Date) | RFP Publish date | Bid Closing date | Tech Bid opening and evaluation (DD/MMM/YY) | Financial Bid Evaluation date (DD/MMM/YY) | Bid Status Successful/ Unsuccessful | Agency/ Vendor selection date | Name of the Agency/Vendor selected | Type of Agency (Not for profit/For Profit) | Date of contract Award | Date of Contract signing | Date of operationalization (DD/MMM/YY) | Budget Source | Contract value (Rs) /year, if applicable | Contract duration (yrs), MOnths, not years | Invoice submission frequency | Time to submit invoice after reporting period (days) | Contract renewal-1 date | No of changes in the contracting terms during renewal-1 | Contract value after renewal-1 | Contract renewal-2 date | No of changes in the contracting terms during renewal-2 | Contract value after renewal-2 | Contract renewal-3 date | No of changes in the contracting terms during renewal-3 | Contract value after renewal-3 | Current status of contract
[26 empty] | Successful |  |  | For Profit | [6 empty] | Annually | [10 empty] | Completed | Accepted
|  |  | ROP | Fee for service | Memorandum of Agreement (MoA) | State | ACSM | CSR | Active case finding and TB prevention | [5 empty] | Operational | RFP preparation | [9 empty] | Unsuccessful |  |  | Not for profit | [6 empty] | Bi-Annually | [10 empty] | Ongoing | Rejected
|  |  | Non ROP | Grant-in-Aid | Memorandum of Understanding (MoU) | District | AIC | DMF | Adherence | [5 empty] | Not operational | RFP published | [19 empty] | Half-yearly | [10 empty] | Terminated
|  |  |  | Hybrid | Service Level Agreement |  | AMC | Loan | Air Borne infection kit | [6 empty] | Pre-bid meeting | [19 empty] | Monthly
|  |  |  | Input | Work order |  | CXR | NHM | Diagnostics | [6 empty] | Bid closing | [19 empty] | No data available
|  |  |  | Non-Financial | Not available |  | DMC | Other | DRTB Consultation | [6 empty] | Technical Evaluation | [19 empty] | Not applicable
|  |  |  | Output |  |  | EPTB | ROP | IEC | [6 empty] | Financial Evaluation | [19 empty] | Others
[7 empty] | FLLPA | State | Innovations | [6 empty] | Agency selected | [19 empty] | Quarterly
[7 empty] | IGRA | XVFC | LT Scheme | [6 empty] | Letter of acceptance
[7 empty] | Others |  | Maintenance | [6 empty] | Retender
[7 empty] | PHA |  | PPSA | [6 empty] | Under renewal
[7 empty] | PPSA |  | Specimen transport | [6 empty] | Not Applicable
[7 empty] | Treatment services |  | Treatment services | [6 empty] | No data available
[7 empty] | TSU |  | X-ray services
[7 empty] | TU |  | Other
Active case finding and TB prevention
CMC
HR Support Services